TECHNOLOGY & PROJECT PROPOSAL

BillionTests

Self-Diagnosis Made Easy

AI-Powered Preventive Health Screening Platform

for Rural & Underserved Communities in Odisha and Eastern India

Submitted to

KIIT-TBI & Bhubaneswar City Knowledge Innovation Cluster (BCKIC) Foundation

An Initiative under the Office of the Principal Scientific Adviser to the Government of India

Submitted by

BillionTests | VisionExcl Technologies Pvt. Ltd.

Pranav Asthana, Co-founder  |  pranav@excl.ai  |  +91 9651891556

billiontests.com  |  Lucknow, India  |  June 2025

1. Problem Statement & Sector Focus

India faces a silent epidemic of preventable chronic diseases. More than 1.4 million lives are lost every year to conditions that are detectable — and largely manageable — through simple, low-cost screening. Yet the vast majority of rural and tribal communities receive no routine diagnostic testing.

| 1.4 M+ Annual avoidable deaths from screenable conditions | 10–20 M DALYs lost annually to late detection |
| --- | --- |
| 12–15% Rural Indians who receive any basic annual test | ~2 Lakh Lives that 50% screening coverage could save annually |

The Disease Burden — Who Is Not Being Screened

| Condition | % of Indian Adults | Annual Testing Rate | Annual Deaths | Avoidable with Early Screening |
| --- | --- | --- | --- | --- |
| Diabetes | ~8–8.3% | 20–25% | ~10,00,000 | 4–6 Lakh |
| Chronic Kidney Disease (CKD) | ~11–16% | <5% | ~1,75,000+ | 1.5–2.5 Lakh |
| UTI (esp. women & elderly) | ~24% women | Variable | Underreported | 1–1.5 Lakh |
| Liver Disease (bilirubinuria) | NAFLD 9–32% | <5% | ~2,68,000 | 10,000–30,000 |
| TOTAL |  |  | >1.4 Million | 6.7–10.8 Lakh |

Why the Gap Persists — Root Causes

- Distance: Rural citizens must travel 20–50 km to reach a diagnostic lab

- Cost perception: Testing seen as unnecessary until symptoms are severe

- Workforce: Doctor and technician shortage at PHCs — care is treatment-focused, not prevention-focused

- Technology: Existing strip readers cost ₹1–2 lakh, are lab-bound, and lock users to proprietary strips

- Speed: Lab results take 24–48 hours — no real-time population-level visibility

Sector Focus

- Primary: Healthcare & Digital Health

- Secondary: Women Empowerment & Livelihoods, Tribal Development, Smart Rural Development

This project directly addresses CSR Schedule VII priorities on Preventive Healthcare, Rural Development, Women Empowerment, and Technology for Social Good.

2. Technology / Solution Overview

BillionTests is: India's first universal AI-powered diagnostic strip reading platform — delivering lab-grade health screening in 20 seconds using smartphone.

The platform combines Computer Vision AI, IoT connectivity, and Blockchain-secured records to transform manual, error-prone strip reading into an instant, trusted, and community-deployable health screening service.

Two Deployment Modes

|  | Mobile App + BT Card™ | Mobile App + BT Card™ + Image Acquisition Box |
| --- | --- | --- |
| How it works | Dip strip in urine, place on BT Card, scan once with smartphone camera. | Insert urine strip into box. Place the smartphone in slot, strip image gets captured strip under controlled lighting. |
| Result time | 20 seconds | < 30 seconds |
| Cost | ₹10 per scan | ₹1,999 one-time + ₹10 per scan |
| Best for | ASHA/ANM workers, health camps, home care, mass screening | PHCs, clinics, NGO camps, corporate wellness |
| Advantage | Mobile only, no devices needed | Handles environmental adversaries during image capturing. |

How BT Card™ Works — The Key Innovation

The BT Card™ is a proprietary reference calibration card printed on standard paper using any printer. It dynamically compensates for differences in smartphone cameras, ambient lighting, strip angle, and strip manufacturer — making AI accuracy consistent regardless of environment. This is what enables 98%+ clinical accuracy without any dedicated hardware.

Health Parameters Detected (10+)

| Parameter | What It Screens For |
| --- | --- |
| Glucose | Diabetes (if >180 mg/dL) |
| Protein | Kidney disease, dehydration, kidney stones |
| Leukocytes (WBC) | UTI, infection, kidney stones |
| Ketones | Diabetes, metabolic disorders |
| Nitrites | Bacterial infection (E. coli, Gonorrhea) |
| Blood (Hematuria) | UTI, kidney stones, intense exercise |
| Urobilinogen | Liver disease, cirrhosis, hepatitis |
| Bilirubin | Early liver disease, bile duct blockage |
| pH (6.7–7.5) | Uric acid stones, protein excess |
| Specific Gravity | Dehydration, concentration issues |

Technology Stack

- Computer Vision AI + Deep Learning — trained on 100,000+ strip images from diverse conditions and lighting

- IoT Connectivity — Bluetooth / Wi-Fi / USB sync with health dashboards and EMR systems

- Blockchain Security — every test result is tamper-proof, linked to time, device ID, and strip type

- Universal Strip Compatibility — works with ALL government-approved strips; no vendor lock-in

- Made in India — 100% indigenously developed; aligns with Atmanirbhar Bharat

3. TRL Stage & Deployment Readiness

Current TRL: TRL 7 — Technology demonstrated and validated in operational environment. Ready for CSR-funded pilot deployment.

| Validation Phase | Activities Completed | Status |
| --- | --- | --- |
| Phase 1 – Core Tech | Mobile app (Android/iOS), hardware, connectivity, GPS, secure data transfer | ✅ Complete |
| Phase 2 – System Reliability | Blockchain integration, cloud load testing, AI model benchmarking vs. experts | ✅ Complete |
| Phase 3 – Controlled Lab Testing | Synthetic urine tests across pH, glucose, salts; reference card validation | ✅ Complete |
| Phase 4 – Field Trials | Multi-city lab validation with real strips; ease-of-use and adoption study | ✅ Complete |
| Phase 5A – Clinical Validation | NABL-accredited City Imaging, Delhi — 98%+ accuracy on 200+ patient samples | ✅ Complete |
| Phase 5B – Clinical Validation | GIMS Greater Noida — Institutional trials (in progress) | 🔄 In Progress |
| Regulatory Prep | MedTech Mitra compliance data; COE-AI IIT Kanpur technical validation; CDSCO prep | 🔄 In Progress |

Credibility & Institutional Support

- Patent Filed — core AI-based strip interpretation and BT Card™ calibration methodology

- Validated at NABL-accredited City Imaging, Delhi — 98%+ accuracy across 10 parameters on 200+ samples

- Incubated at GIMS Greater Noida — clinical trial support and regulatory navigation

- Technical validation by COE-AI, IIT Kanpur — AI model architecture and system design

- Regulatory guidance from MedTech Mitra, Government of India

4. Key Innovation & Differentiators

| Innovation Pillar | BillionTests | Competing Solutions |
| --- | --- | --- |
| Device Cost | ₹1,999 (Edge Device) | ₹1–2 lakh (Siemens, Roche, Abbott, Menarini) |
| Scan Cost | ₹10 per scan | ₹50–200 per lab test |
| Strip Compatibility | Universal — any govt-approved strip | Proprietary strips only |
| AI Interpretation | 98%+ validated accuracy | NA |
| Blockchain Reports | Yes — tamper-proof, CSR-auditable | No |
| Result Time | < 30 seconds | 24–48 hours (lab) or 60–90 sec (imported device) |
| Origin | 100% Made in India | Predominantly foreign brands |
| CSR Impact Reporting | Auto-generated blockchain-verified PDFs | Manual, non-verifiable |

Why This Matters for CSR Programs Specifically

- Blockchain-verified impact reports eliminate audit uncertainty — every test is independently verifiable

- Auto-generated CSR compliance documentation reduces partner reporting burden significantly

- Works with ASHA workers and Anganwadi workers with zero medical training — half-day orientation suffices. The app uses icon-based, step-by-step guidance in regional languages, requires no typing, and completes a full screening in under 20 seconds on any basic Android smartphone. No electricity, Wi-Fi, or lab equipment needed — operable directly at Anganwadi centres, panchayat halls, and sub-health centres. Results are auto-shared in the user’s preferred language via WhatsApp or printed QR-linked summaries.

- No infrastructure dependency — works in the most remote tribal blocks without electricity or internet

- Lean unit economics: cost per screening drops to < ₹15 at 10,000+ test scale, enabling massive reach per rupee of CSR spend

5. Target Beneficiaries & Geography

Primary Beneficiaries

- Women — especially those at risk for UTI, pregnancy complications, and early-stage kidney disease

- Elderly population (60+) — diabetes (25–30%), CKD (20–30%), UTI (15–25%), dehydration (30–40%)

- Diabetic-risk individuals — undiagnosed pre-diabetics in Tier 3–6 towns and rural areas

- Tribal communities in Odisha — Koraput, Malkangiri, Rayagada, Sundargarh districts

- Low-income households — first access to any form of routine health screening

Delivery Model — Two Parallel Channels

Channel A: BillionTests-staffed weekly health camps — company ground staff operate camps directly at 50 community locations on a rotation basis (2 locations active concurrently at any time).

Channel B: Independent public/private health centre network — BillionTests Image Acquisition Systems deployed at 50 health centres where staff self-scan independently, expanding reach between camp rotations.

| Channel | Operator | Locations | Frequency | Oversight |
| --- | --- | --- | --- | --- |
| A: BillionTests Health Camps | BillionTests ground staff (2 dedicated staff) | 50 community sites on rotation | Weekly camps; 2 locations concurrent at any time | Direct — BillionTests quality control |
| B: Health Centre Network | Public/private health centre staff (self-operated) | 50 health centres | Continuous, as per centre footfall | Remote — app-guided; blockchain-verified results |

Priority Geography

| Priority | Geography | Rationale |
| --- | --- | --- |
| Phase 1 | Odisha — tribal districts (Koraput, Malkangiri, Rayagada, Sundargarh) and coastal communities | BCKIC priority state; highest unmet screening need |
| Phase 2 | Eastern India — Jharkhand, West Bengal, Chhattisgarh | Adjacent tribal belts; CSR partner footprints (NALCO, JSPL, Vedanta) |
| Phase 3 | Pan-India scale-up via NHM and CSR partner networks | Replicable model; national CSR programs |

6. Expected Impact & Measurable KPIs

Pilot-Period Health Outcomes (12 months, 2 channels combined)

| 50,000+ Total individuals screened (both channels) | 50 Health centres equipped (Channel B) |
| --- | --- |
| 50 Community locations covered | 2,000+ Estimated diabetes-risk cases identified |

| Health Outcome | Channel A (Health Camps) | Channel B (Health Centres) | Combined Target |
| --- | --- | --- | --- |
| Individuals screened | ~25,000 | ~25,000 | 50,000+ |
| Diabetes-risk cases identified | ~1,000 | ~1,200 | 2,200+ |
| CKD / kidney-risk cases | ~700 | ~800 | 1,500+ |
| UTI and infection cases flagged | ~1,500 | ~1,800 | 3,300+ |
| Dehydration / nutrition-risk alerts | ~1,200 | ~1,500 | 2,700+ |
| Liver health abnormalities flagged | ~300 | ~400 | 700+ |

Measurable KPIs for BCKIC / CSR Reporting

| KPI | Target (12-month Pilot) | Measurement Method |
| --- | --- | --- |
| Total individuals screened (both channels) | ≥ 50,000 | Blockchain-verified count |
| BillionTests health camp locations covered | 50 community sites | Field coordinator log + geo-tagged check-ins |
| Weekly health camps conducted | ≥ 100 camps (2/week across rotation) | Camp attendance register + scan logs |
| Health centres equipped & active (Channel B) | 50 centres | Device deployment log + activation report |
| Cost per individual screened | < ₹50 | Budget vs. screens completed |
| Test accuracy vs. lab reference | ≥ 95% concordance | Parallel lab sample comparison |
| Average result delivery time | < 30 seconds | App telemetry data |
| % cases referred for follow-up care | Track and report | Referral slip + follow-up call |
| Blockchain-verified reports generated | 100% of all tests | Blockchain ledger |
| CSR impact reports delivered | Monthly + Quarterly + Annual | Automated report generation |

ESG & SDG Alignment

| Framework | Alignment |
| --- | --- |
| CSR Schedule VII | Preventive Healthcare ✔ ¦ Rural Development ✔ ¦ Women Empowerment ✔ ¦ Technology for Social Good ✔ |
| SDG 3 | Good Health & Well-being — early disease detection at community level |
| SDG 5 | Gender Equality — prioritises women's health; direct outreach through BillionTests ground teams |
| SDG 9 | Industry, Innovation & Infrastructure — Made-in-India AI deployed for public good |
| SDG 10 | Reduced Inequalities — bridges urban-rural diagnostic gap for underserved communities |
| ESG — Social | Healthcare access, inclusion, and reduction of preventable disease burden |
| ESG — Governance | Blockchain-based transparency; fully audit-ready CSR reporting |
| ESG — Environmental | Reduces patient travel; digital-first reporting; minimal infrastructure footprint |

Societal Impact — Society, Women & Rural Communities

Impact on Society

BillionTests addresses one of India’s most critical public health failures: the near-complete absence of preventive health screening in underserved communities. By deploying AI-powered diagnostics at the community level, the platform enables early detection of diabetes, kidney disease, UTIs, and liver conditions — conditions that are silent until they become life-threatening. This shifts the healthcare paradigm from reactive, high-cost treatment to proactive, low-cost prevention. At 50,000+ screenings per year, BillionTests prevents an estimated 2,000+ individuals from progressing to advanced-stage disease, reducing hospitalisation burden on the public health system and generating significant societal savings in lost productivity and avoidable mortality.

Impact on Women

Women in rural India bear a disproportionate burden of undiagnosed disease. Approximately 24% of rural women experience UTIs annually, while pregnancy-related kidney and glucose complications remain largely undetected due to absence of affordable, accessible testing. BillionTests specifically prioritises women in its outreach model: health camps are deployed at Anganwadi centres, self-help group (SHG) meetings, and women’s panchayat sessions — spaces where women already gather. Screening is non-invasive, takes under 20 seconds, and is conducted with dignity in community settings. By bringing diagnostics directly to women rather than requiring them to travel 20–50 km to labs, BillionTests removes the two primary barriers: cost and mobility. Women also gain a printed, blockchain-secured health record — many for the first time in their lives — enabling continuity of care during referrals and pregnancies.

A Critical Problem Solved: Pregnancy Monitoring & ASHA Workers

ASHA workers today conduct urine strip tests for pregnant women as part of ANC (Antenatal Care) protocols — but the process is deeply flawed. The conventional method requires the worker to manually match wet strip colours against an 80-shade printed colour chart, often under poor lighting conditions, in homes or outdoors. This process is error-prone (colour perception varies by person, lighting, and strip age), time-consuming (taking 3–5 minutes per reading vs. 20 seconds with BillionTests), and frequently leads to misclassification of glucose or protein levels that are critical indicators during pregnancy. A missed positive on gestational diabetes or preeclampsia (detected via protein in urine) can have life-threatening consequences for the mother and foetus. BillionTests eliminates this entirely: the AI reads the strip with 98%+ accuracy in 20 seconds — removing human subjectivity, colour-chart dependency, and reporting errors from the most critical touchpoint in rural maternal health.

Non-Invasive Testing: A Game-Changer vs. Blood-Based Diagnostics

Conventional blood-based diagnostic testing — the current standard — is invasive, inconvenient, and logistically prohibitive for rural and underserved communities. Blood draws require trained phlebotomists, sterile needles, cold-chain storage (blood samples must be kept at 2–8°C), and timely transport to labs — a complex chain that breaks down constantly in rural India. For many patients, particularly women and the elderly, needles are a source of genuine fear and avoidance, resulting in large-scale non-compliance with recommended tests. Blood tests also require fasting (for glucose), limiting when and where they can be conducted. BillionTests urine-based screening requires none of this: the patient simply dips a strip in a fresh urine sample (first-morning urine is NOT required — any time of day works), places it on the BT Card, and scans with a smartphone. No needles. No cold chain. No fasting. No lab. No wait. Result in 20 seconds, anywhere, anytime. This is what makes community-level mass screening genuinely possible for the first time.

Special Focus: Pregnant Women & Women 50+ — The Highest-Need Cohorts

BillionTests is a transformative tool for two critically underserved female cohorts: (1) Pregnant women, for whom routine urine screening is already mandated under ANC protocols but rarely conducted accurately due to the colour-chart problem described above. Gestational diabetes affects 10–14% of Indian pregnancies; preeclampsia (protein in urine) affects 5–8% and is a leading cause of maternal mortality. BillionTests enables every ANC visit to include an accurate, instant urine screen — at a cost of ₹10 per test. (2) Women aged 50+ face a convergence of three highly prevalent and largely silent conditions: UTI (affecting 30–40% of post-menopausal women annually), Type 2 diabetes (20–25% prevalence), and early chronic kidney disease (15–20% prevalence). These conditions are interconnected — untreated UTI accelerates kidney damage in diabetic women — and BillionTests screens all three simultaneously in a single 20-second test. In a country where women routinely deprioritise their own health, an accessible, non-invasive, instant, and community-delivered screening is not just convenient — it is the only approach that will achieve actual uptake.

Impact on Rural Areas

For rural India, BillionTests operates as a “diagnostic infrastructure layer” that previously did not exist. Tribal districts such as Koraput, Malkangiri, Rayagada, and Sundargarh (Odisha) have virtually no routine screening infrastructure — the platform fills this gap without requiring hospitals, labs, or trained medical professionals. Panchayat-level implementation creates a permanent, rotating community health touchpoint that improves health literacy, encourages preventive behaviour, and generates real-time population health data that district health authorities can act upon. The result is measurable improvement in rural health outcomes at the block and panchayat level — contributing to district-level NHM targets and enabling data-driven public health planning.

Why BillionTests is Near-Perfect for Rural India

Every constraint of rural India has been accounted for in BillionTests’ design. The platform requires no electricity (smartphone battery only), no internet (offline-first; syncs when connectivity is available), no cold chain (urine strips are stable at room temperature), no lab (results delivered on-device), no trained medical staff (icon-guided app in regional languages; half-day training), no expensive hardware (any Android phone; ₹1,999 optional box), and no first-morning urine (any-time sample is sufficient). The entire user journey — from strip dip to result to blockchain-secured digital record — takes under 30 seconds and can be conducted at an Anganwadi centre, a panchayat building, a home visit, or a roadside health camp. This is health infrastructure that goes to the patient, rather than requiring the patient to travel to it. In a country where the average rural resident lives 20–50 km from a diagnostic lab, this is not an incremental improvement — it is a fundamentally different paradigm. The simplicity is deliberate and complete: there is virtually no barrier remaining between a rural individual and an accurate health screening.

7. Implementation Model & Deployment Requirements

Pilot Design: A 12-month, dual-channel deployment across 100 touchpoints (50 community camp sites + 50 health centres) in Odisha and Eastern India — operated directly by BillionTests ground staff and empowered health centre partners — targeting 50,000+ individuals screened with real-time blockchain-verified impact reporting.

Channel A: BillionTests-Staffed Weekly Health Camps

BillionTests deploys 2 dedicated trained ground staff who operate health screening camps directly at community locations — without any dependency on ASHA workers, Anganwadi staff, or PHC infrastructure. This ensures consistent quality, controlled throughput, and direct accountability.

| Parameter | Details |
| --- | --- |
| Total locations | 50 community sites (villages, panchayat centres, community halls, market areas) |
| Concurrent active locations | 2 locations running simultaneously at any time |
| Rotation cycle | Each location covered once every 4 weeks |
| Camp frequency | Weekly camps at each active location; |
| Staffing | 2 BillionTests-employed field health technicians (full-time, dedicated) |
| Camp setup | Portable screening station: device, BT Cards, strips, branded banners, referral forms |
| Screening process | Walk-in model; 10–15 minute per individual; results delivered on-site via app |
| Referral linkage | All abnormal results provided a referral card to nearest PHC/specialist |

Channel B: Independent Health Centre Network

BillionTests provides Image Acquisition Systems (devices) to 50 empanelled public and private health centres. Centre staff are trained once (half-day) and thereafter scan independently — extending programme reach continuously between health camp rotations.

| Parameter | Details |
| --- | --- |
| Total health centres | 50 public / private centres empanelled across the pilot geography |
| Device per centre | 1 BillionTests Image Acquisition System (₹1,999) — one-time, unlimited scans |
| Strips supplied | Initial stock of 200 strips per centre; replenished monthly based on usage |
| Training | Half-day onboarding per centre; app is self-guided; no medical training required |
| Monitoring | Remote — all results auto-uploaded to cloud; blockchain-verified; visible on dashboard |
| Support | WhatsApp/call support from BillionTests team; monthly field visit per centre |

Future Distribution Channels — All Routes to Market

BillionTests is designed as a multi-channel platform that can penetrate the healthcare ecosystem at every level — from the village ASHA worker to the national NHM infrastructure. The table below maps all active and planned distribution channels, the specific deployment model for each, and the scale potential they represent.

| Channel | Deployment Model & Details | Scale Potential | Timeline |
| --- | --- | --- | --- |
| 1. ASHA Workers (ANC & Village Level) | 10.4 lakh ASHA workers across India already conduct urine strip tests during ANC home visits. BillionTests replaces the error-prone 80-shade colour chart with instant AI reading on their existing smartphones. No new device required — just the app + BT Card. NHM can mandate at state level as part of ANC protocol upgrade. | 10.4L workers; 2–5 tests/worker/week = 10Cr+ tests/year | Year 2–3 (NHM empanelment) |
| 2. Anganwadi Centres (ICDS / WCD) | 13.9 lakh Anganwadi centres are the primary touchpoint for women and children in rural India. AWWs (Anganwadi Workers) conduct routine health monitoring — BillionTests integrates as the urine screening tool at every ANC session and nutrition camp. State WCD departments procure strips; BillionTests provides platform as a managed per-district subscription. | 13.9L centres; 5–10 tests/week each = 7–14Cr tests/year | Year 2–3 |
| 3. Primary Health Centres (PHCs) & Sub-Centres | 25,000+ PHCs and 1.6 lakh sub-centres are the backbone of rural healthcare. BillionTests Image Acquisition Systems are deployed at PHC OPD for routine urine screening of all walk-in patients — replacing manual strip reading and reducing diagnostic errors. Results feed directly into health records and NHM dashboards. | 25K PHCs + 1.6L sub-centres; 20–50 tests/day each | Year 1–2 (NHM pilot empanelment) |
| 4. NHM (National Health Mission) — State & District Programs | NHM’s Reproductive and Child Health (RCH) program mandates ANC urine testing. BillionTests seeks empanelment as an NHM-approved diagnostic tool, enabling per-test government reimbursement. Integration with Ayushman Bharat Digital Mission (ABDM) enables test results to link directly to patients’ ABHA health IDs, creating longitudinal health records for rural beneficiaries. | National scale; govt-funded recurring revenue | Year 2–3 |
| 5. CSR-Sponsored Health Camps (Corporate + Foundation) | Corporate CSR partners (NALCO, JSPL, Vedanta, Pernod Ricard, Bayer etc.) fund BillionTests-operated health camps in their impact geographies. BillionTests provides turnkey execution — staff, devices, strips, reporting — and delivers blockchain-verified CSR impact reports. Partners get Schedule VII compliance documentation and brand presence at community level. | 50K–5L tests per CSR partner per year | Year 1 (active) |
| 6. BillionTests Self-Operated Health Camps | BillionTests ground staff operate weekly camps at community sites (villages, market areas, panchayat halls) on a rotation model. 2 dedicated field technicians cover 50 locations with 2 concurrent active sites at any time. Rotation cycle: each location covered once every 4 weeks. Direct quality control and accountability. | 25K tests/year per 2-staff team | Year 1 (active) |
| 7. Private Clinics & General Practitioners (GPs) | 6+ lakh private clinics and GPs in Tier 2–6 cities and rural India currently send urine samples to external labs (24–48 hour TAT, ₹100–200 per test). BillionTests enables in-clinic instant results at ₹10 strip cost — clinics can charge ₹30–50 per test and earn a margin. The Image Acquisition Box (₹1,999 one-time) pays back within 200 tests. No contract, no lock-in. | 6L clinics; 5–20 tests/day each | Year 1–2 (B2B sales) |
| 8. Diagnostic Labs (as an Add-on Service) | Standalone diagnostic labs use BillionTests as a faster, lower-cost front-end for urine analysis — delivering instant preliminary results while confirmatory tests are processed. Labs benefit from faster throughput and patient experience. Particularly relevant for labs in Tier 3–6 towns serving high patient volumes. | 1L+ diagnostic labs; 50–200 tests/day each | Year 2–3 |
| 9. Corporate Wellness (Employee Health Programs) | Large employers (mining, manufacturing, agriculture processing) with workforces in rural / semi-urban India purchase annual screening programmes for employees and dependent family members. NALCO, JSPL, SAIL plant sites are priority targets — aligning with their own CSR health commitments for worker communities. | 500–50K employees per corporate client | Year 1–2 |
| 10. NGO & Development Organisation Programmes | INGOs (PATH, PSI, CARE, Americares) and domestic NGOs (Jan Swasthya Sahayog, Ekjut, Samaj Pragati Sahayog) running community health programmes in tribal and rural areas integrate BillionTests as their urine screening tool — replacing manual strip reading and lab referrals. Grant-funded procurement; NGO distributes strips; BillionTests provides platform and training. | 10K–5L tests per NGO per year | Year 1–2 |
| 11. Dairy / Agricultural Extension Networks | Strategic partner Prompt Dairy Tech (70,000 villages, 15 crore cattle) provides a unique last-mile distribution channel: rural dairy collection agents who visit every village daily become BillionTests strip distributors and can facilitate screening. AMUL and Hatsun milk collection centres (reached by BillionTests’ existing Tracksure relationship) serve as low-cost fixed screening points in agricultural communities. | 70K villages; unique rural last-mile reach | Year 2–3 |
| 12. Telemedicine & Digital Health Platforms | Integration with telemedicine platforms (eSanjeevani, Practo, mFine, Docsapp) enables at-home test + remote consultation workflows: patient performs strip test at home, result is shared with the remote doctor before the telemedicine consultation — enabling evidence-based remote diagnosis without lab visits. API integration provides direct feed into consultation records. | 10Cr+ eSanjeevani consultations/year addressable | Year 2–3 |

Collectively, these 12 channels represent a Total Addressable Market (TAM) of 1 billion+ urine strip tests annually in India — currently conducted manually, inaccurately, or not at all. BillionTests is positioned as the universal platform across all of them, with the same AI engine, same BT Card, and same blockchain backend enabling consistent accuracy and reporting regardless of the channel.

Phase-wise Execution Plan

| Phase | Duration | Key Activities |
| --- | --- | --- |
| Phase 1: Setup & Mobilisation | Month 1 | Site survey and selection of 50 camp locations + 50 health centres; procurement of devices, strips, BT Cards; branded campaign material printing; hiring and training of 2 ground staff; health centre onboarding; digital dashboard setup |
| Phase 2: Pilot Launch | Month 2 | First health camps activated at 2 locations concurrently; first batch of health centres begin independent scanning; community awareness campaigns launched (posters, local announcements, social media) |
| Phase 3: Full Operation | Months 2–10 | Weekly health camps on rotation across all 50 locations; continuous screening at health centres; weekly data review; monthly CSR impact reports generated; referral tracking; mid-pilot review at Month 6 |
| Phase 4: Scale-up Planning | Month 11–12 | Deep-dive impact analysis; blockchain-verified annual impact report; media kit prepared; scale-up proposal for Year 2 submitted to BCKIC/CSR partners |

Deployment Requirements

| Requirement | Details |
| --- | --- |
| Devices (Channel B) | 50 BillionTests Image Acquisition Systems for health centre network |
| Devices (Channel A) | 2 portable devices for ground staff use at health camps |
| Diagnostic Strips | ~55,000 strips for 12 months across both channels |
| BT Cards | Printed on laminated/plastic sheets for durability; replenished quarterly |
| Ground Staff | 2 full-time BillionTests-employed field health technicians (hired, trained, managed by BillionTests) |
| Campaign Materials | Branded banners, flex prints, leaflets, referral forms — produced centrally, deployed at all sites |
| Cloud & Reporting | Automated blockchain-verified reports; real-time dashboard access for BCKIC/CSR partner |
| Connectivity | Offline-first; syncs via any mobile data connection; no Wi-Fi infrastructure required |

8. Previous Pilots & Deployments

Validation Milestone: Clinically validated at NABL-accredited City Imaging, Delhi — 98%+ accuracy across 10 parameters on 200+ real patient urine samples.

Completed Validations

| Validation | Institution / Partner | Outcome |
| --- | --- | --- |
| Clinical Accuracy Trial | City Imaging, Delhi (NABL-accredited) | 98%+ accuracy on 200+ real patient samples across 10 parameters |
| AI Model Benchmarking | COE-AI, IIT Kanpur | Trained on 100,000+ images; validated against expert manual reading |
| Controlled Lab Testing | Internal (synthetic urine) | Chemical variation testing across pH, glucose, salts, and all 10 parameters |
| Multi-City Field Trials | Diagnostic labs across multiple cities | Real-world lighting, multiple strip brands, diverse demographic groups |
| User Adoption Study | Field health workers | Ease of use; average onboarding time < 2 hours; adoption rate > 90% |

Institutional Support

- GIMS Greater Noida — incubation centre support; ongoing institutional clinical trials; CDSCO compliance navigation

- MedTech Mitra (GoI) — regulatory standards guidance and compliance documentation

- Strategic Partnership: Prompt Dairy Tech — access to 70,000 villages and 15 crore cattle for veterinary extension

Team Credibility

BillionTests is built by an IIT Kanpur and IIT Jodhpur alumni team with 10+ years of deep AI and computer vision experience and a track record of deploying AI at national scale:

| Product / Platform | What It Does | Clients / Scale |
| --- | --- | --- |
| Checko.ai | Anti-counterfeiting AI — 1-in-a-million failure rate, works on any smartphone | Amazon, IOCL, Delhi Excise, Security Press of India |
| Upjao.ai | AI-powered grain quality assessment — detects defects across grain types | ITC FBD, Tata FDRVC, Adani Wilmar, Reliance Foundation |
| Tracksure | Computer vision crate tracking for dairy networks | Amul, Hatsun |

| Team Member | Role | Background |
| --- | --- | --- |
| Pranav Asthana | Co-founder, Business | M.Tech. IIT Kanpur; Founded Checko, Upjao, Schozzle |
| Ritu Mishra | Co-founder, Product | Ex-Researcher IIT Kanpur; Built 5+ deep-tech products |
| Mohini Behera | Co-founder, Tech | B.Tech. NIT Rourkela; Built 10+ AI products |
| Prof. Amitabha Bandyopadhyay | Advisor | BSBE, IIT Kanpur; Ex-Harvard Medical School |
| Neeraj Garg | Advisor | Ex-CTO AMUL & NDDB; 25+ years in tech strategy |
| Dr. Ravi Vedururu | Medical Advisor | PhD; Clinical Diagnostics & Medical Device Consultant |

9. Budget Requirement & Timeline

Pilot Scope: 50 community camp locations + 50 health centres ¦ 50,000+ individuals screened ¦ Odisha / Eastern India ¦ 12 months ¦ Total Budget: ₹25 Lakh

A. Hardware & Consumables

| Item | Specification | Qty | Unit Cost | Total (₹) |
| --- | --- | --- | --- | --- |
| BillionTests Image Acquisition Systems — Health Centres (Ch. B) | One per health centre | 50 | ₹1,999 | ₹99,950 |
| BillionTests Image Acquisition Systems — Ground Staff (Ch. A) | For field health technicians | 2 | ₹1,999 | ₹3,998 |
| Diagnostic Test Strips | Govt-approved; 12-month supply for both channels | 55,000 strips | ₹10 | ₹5,50,000 |
| BT Cards (laminated / plastic sheet) | Durable outdoor-grade; quarterly replenishment | 5,000 cards | ₹6 | ₹30,000 |

B. Ground Operations — Dedicated Manpower

| Item | Specification | Duration | Monthly Cost | Total (₹) |
| --- | --- | --- | --- | --- |
| Field Health Technician #1 | Full-time; operates health camps at 50 locations on rotation; trained by BillionTests | 12 months | ₹20,000/month | ₹2,40,000 |
| Field Health Technician #2 | Full-time; co-operates camps; manages health centre support visits | 12 months | ₹20,000/month | ₹2,40,000 |
| Field Coordinator / Programme Manager | Oversees both channels; data review; partner liaison; reporting | 12 months | ₹35,000/month | ₹4,20,000 |

C. Campaign, Awareness & Community Mobilisation

| Item | Specification | Total (₹) |
| --- | --- | --- |
| Community Awareness Campaign — Print | Posters, leaflets, referral forms (per location per camp); 50 locations × 12 months | ₹1,20,000 |
| Branded Camp Setup Material | Flex banners (6×4 ft), standees, BillionTests branded kits per camp location | ₹75,000 |
| Local Mobilisation — Community Outreach | Gram sabha announcements, local NGO liaison, religious/community leader engagement per site | ₹90,000 |
| Digital & Social Media Campaign | Facebook/WhatsApp community targeting in pilot geographies; 12-month campaign | ₹60,000 |
| Health Centre Onboarding Kits | Welcome pack, instruction cards, strip storage, branded material per centre | ₹50,000 |

D. Travel, Logistics & Field Operations

| Item | Specification | Total (₹) |
| --- | --- | --- |
| Ground Staff Travel | Fuel/transport for 2 staff rotating across 50 locations for 12 months | ₹1,80,000 |
| Strip & Device Distribution Logistics | Bulk delivery to 50 health centres + ongoing replenishment | ₹60,000 |
| Monthly Health Centre Field Visits | 1 coordinator visit/month × 50 centres over 12 months (batched) | ₹60,000 |

E. Technology, Cloud & Reporting

| Item | Specification | Total (₹) |
| --- | --- | --- |
| Cloud Infrastructure & Blockchain (12 months) | Server, storage, API calls, blockchain transaction costs for 50,000+ tests | ₹1,20,000 |
| Real-Time CSR Dashboard (custom for partner) | Partner-branded live dashboard; role-based access for BCKIC and CSR partner | ₹60,000 |
| Impact Report Design & Production | Monthly + quarterly + annual CSR reports; branded; print-ready PDFs | ₹60,000 |
| Media & Communication Kit | Photography, video documentation of health camps for partner ESG communication | ₹40,000 |

F. Contingency & Miscellaneous

| Item | Total (₹) |
| --- | --- |
| Programme contingency (unforeseen logistics, equipment, staff) | ₹80,000 |
| Miscellaneous (stationery, data entry, minor repairs) | ₹30,000 |

| TOTAL PROGRAMME BUDGET (12 months) | ₹25,00,000 (₹25 Lakh) |
| --- | --- |
| A. Hardware & Consumables | ₹6,83,948 |
| B. Dedicated Ground Manpower (3 staff × 12 months) | ₹9,00,000 |
| C. Campaign, Awareness & Community Mobilisation | ₹3,95,000 |
| D. Travel, Logistics & Field Operations | ₹3,00,000 |
| E. Technology, Cloud & Reporting | ₹2,80,000 |
| F. Contingency & Miscellaneous | ₹1,10,000 |

Milestone Timeline

| Milestone | Target |
| --- | --- |
| Proposal selection & MoU signing | Month 0 |
| Site survey, procurement, staff hiring & training | Month 1 |
| Health centre onboarding (50 centres) | Month 1–2 |
| Campaign material production & distribution | Month 1 |
| Pilot launch — first health camps + health centres active | Month 2 |
| Full rotation operational (all 50 locations in schedule) | Month 3 |
| Mid-pilot CSR impact report delivered to partner | Month 6 |
| Blockchain-verified annual impact report + media kit | Month 12 |
| Scale-up proposal for Year 2 submitted | Month 12–13 |

9A. Detailed Cost & Revenue Structure Forecast

A. Complete Cost Structure — One-Time & Recurring

BillionTests’ cost structure separates clearly into one-time capital investments (already made or near-complete) and recurring operational costs per test — enabling a scalable economics model where unit costs fall sharply as volume grows.

| Cost Component | Description | Type | Cost |
| --- | --- | --- | --- |
| AI Model Development | Computer vision AI trained on 100K+ strip images; multi-parameter deep learning model; BT Card calibration algorithm; validated at NABL lab. Already completed. No further R&D capex required for scale. | ONE-TIME (done) | ₹0 additional (sunk cost; amortised over all future tests) |
| Image Acquisition Box | Controlled-lighting hardware box for high-accuracy strip imaging; deployed at health centres and PHCs. Optional for ASHA/Anganwadi (app-only mode sufficient). Durable; 3–5 year lifespan; unlimited scans. | ONE-TIME (per site) | ₹1,999 per device. At 10,000 tests/device over lifespan = ₹0.20/test amortised |
| Diagnostic Strip (per test) | Government-approved 10-parameter urine test strip. Universal compatibility — no proprietary lock-in. Bulk procurement cost reduces significantly at volume. Pilot: ₹10; at 10L+ strips/year: ₹5–6; at 1Cr+ strips/year: ₹3–4. | RECURRING (per test) | ₹3–10 per test (volume-dependent; target: ₹3 at scale) |
| BT Card (per test, amortised) | Proprietary reference calibration card printed on laminated/plastic sheet. One BT Card can be used for ~50 tests before replacement. Printable on any standard printer. Quarterly replenishment. Laminated card cost: ₹6; amortised over 50 tests = ₹0.12/test. | RECURRING (periodic) | ₹0.12/test |
| Cloud Platform & Maintenance | AWS/GCP server costs; blockchain transaction fees; API calls; AI inference compute per scan; app hosting; dashboard delivery; ongoing model updates & retraining; security & compliance. Cost falls sharply with volume due to fixed infrastructure base. | RECURRING (per test, declining) | ₹2.40/test at 50K tests; ₹0.80/test at 5L tests; ₹0.30/test at 50L tests |
| Manpower (CSR-funded camps) | Field technicians for BillionTests-operated health camps (Channel A). Funded by CSR grant in pilot. At scale via ASHA/Anganwadi channels, manpower cost is near-zero as existing frontline workers operate the platform within their existing duties. | RECURRING (camp-funded) | ₹18/test (pilot camps); ₹0–2/test (ASHA/Anganwadi channel at scale) |

B. Unit Cost Target: <₹5 per Test — Sell at ₹10 — Social & Commercial Viability

BillionTests’ core goal is to bring total all-in cost per test below ₹5 at scale — making it the lowest-cost clinical-grade health screening in India — while selling to end users (patients, health centres, CSR partners) at ₹10 per test. This creates a ₹5 gross margin per test that funds platform sustainability, expansion, and impact reporting. The path from current pilot unit economics to the <₹5 target is entirely driven by volume — no new technology development is required.

| Cost Element | 50K tests (Pilot) | 5L tests (Yr 2) | 50L tests (Yr 3) | 5Cr tests (Yr 5) |
| --- | --- | --- | --- | --- |
| Strip cost | ₹10.00 | ₹6.00 | ₹4.00 | ₹3.00 |
| BT Card (amortised) | ₹0.12 | ₹0.12 | ₹0.10 | ₹0.08 |
| Cloud + AI inference | ₹2.40 | ₹0.80 | ₹0.40 | ₹0.20 |
| Device amortised (box) | ₹0.40 | ₹0.20 | ₹0.10 | ₹0.04 |
| Manpower | ₹18.00 (dedicated staff) | ₹1.50 (existing workers) | ₹0.80 | ₹0.40 |
| TOTAL COST PER TEST | ~₹31 | ~₹8.62 | ~₹5.30 ✔ TARGET | ~₹3.68 ✔✔ ACHIEVED |
| SELLING PRICE (to customer) | ₹10 (CSR-subsidised) | ₹10 | ₹10 | ₹10 |
| GROSS MARGIN PER TEST | −₹21 (CSR-funded) | +₹1.38 (break-even) | +₹4.70 (profitable) | +₹6.32 (highly profitable) |

C. Revenue Forecast & Corresponding Social Impact

| Year | Tests Conducted | Gross Revenue (@ ₹10) | Net Margin | Individuals Benefited | Disease Cases Caught Early |
| --- | --- | --- | --- | --- | --- |
| Year 1 (Pilot) | 50,000 | ₹5 Lakh | −₹10.5L (CSR-funded) | 50,000+ | 7,700+ (diabetes, CKD, UTI, liver) |
| Year 2 | 5 Lakh | ₹50 Lakh | +₹6.9L (near break-even) | 5 Lakh+ | 77,000+ cases detected |
| Year 3 | 50 Lakh | ₹5 Crore | +₹2.35Cr (unit economics <₹5 ✔) | 50 Lakh+ | 7.7L+ cases; 50K+ lives saved |
| Year 5 | 5 Crore | ₹50 Crore | +₹31.6Cr (highly profitable) | 5 Crore+ | 77L cases; 5L+ lives saved annually |

By Year 3, BillionTests achieves its core unit economics target: all-in cost per test below ₹5, selling at ₹10, generating a ₹4.70+ gross margin that funds both business sustainability and CSR-free expansion. By Year 5 at 5 crore tests annually, the platform becomes one of India’s largest preventive health infrastructure programmes — commercially self-sustaining, saving an estimated 5 lakh lives annually, and generating ₹50 crore in annual revenue. The AI development cost (one-time, already incurred) is fully amortised across billions of future tests, making BillionTests one of the highest-leverage investments in Indian public health.

10. Support Expected from BCKIC / CSR Partners

From BCKIC

- Facilitation of access to 50 community sites and 50 health centres in Odisha and Eastern India — introductions to district health offices, panchayat bodies, and NGO partners

- Introductions to aligned CSR/ESG corporate partners — NALCO Foundation, JSPL Foundation, Pernod Ricard Foundation, Bayer Foundation — for programme funding (₹25 lakh)

- Ecosystem validation and co-branding on impact reports — strengthens CSR partner Schedule VII compliance documentation

- Support in regulatory and state health department engagement for health centre network empanelment

- Mentorship for scale-up pathways from pilot to multi-district / national deployment

From CSR Partners

- Programme grant of ₹25 lakh structured as CSR Schedule VII healthcare expenditure — preventive health + rural development + technology for social good

- Access to community footprint in Odisha (existing CSR geographies, village adoption programmes, employee health camp networks)

- Co-branding rights on all health camp materials, screening reports, digital communications, and ESG reports

- Facilitation of partnerships with local NGOs, Gram Panchayats, and community leaders for camp mobilisation

What BillionTests Delivers in Return

| Deliverable | Details |
| --- | --- |
| Monthly Impact Dashboard | Live web dashboard — screenings by location, disease trends, demographics, geography maps |
| Quarterly CSR Report | Partner-branded; CSR Schedule VII compliant; blockchain-verified screening numbers. Delivered as professionally formatted PDF documents — print-ready for board presentations, regulatory submissions, and CSR committee reviews. |
| Annual Impact Report | Full outcome analysis; case studies; referral outcomes; scale-up recommendations |
| Blockchain-Verified Data | 100% of tests tamper-proof — eliminates audit risk for partner; independently verifiable |
| Health Camp Brand Presence | CSR partner logo on all camp materials, banners, BT Cards, and digital content |
| Media & Communication Kit | Photos, videos, beneficiary testimonials from 50 locations for partner ESG comms |
| Scale-up Roadmap | Data-driven Year 2 proposal for district-level rollout with refined cost model |

BillionTests — Early Detection. Lower Costs. Healthier Lives.

Pranav Asthana  |  pranav@excl.ai  |  +91 9651891556  |  billiontests.com

Patent Pending | Validated at NABL-accredited Lab | Incubated at GIMS Greater Noida | IIT Kanpur Alumni Team